## ★ FIX LIST (scan)
ENGINEER FIX LIST — prioritized, from a deterministic scan of ALL 40 lessons (1,023 rows)
Full-module scan complete. Priorities below are confirmed across Units 1–3.
NOTE: of 46 P8 rows, only ~13 have a cleanly parseable intended label — the other 33 need the engine re-ground to recover the right label, which is why the fix belongs in the re-run, not a hand-patch.
# | Issue | Evidence (40-lesson scan) | Fix | Hand-fixable?
1 | Grounding rejections (46 rows) — CORRECTED into 3 causes: (a) 17 concatenation false-positives (real quotes joined by ';'/'…' → guard over-rejects → safe to restore); (b) 10 model inserted [editorial notes]/paraphrase into the evidence → guard CORRECTLY rejects (dirty citation); (c) 19 'clean' single quotes that still failed → need per-quote verification (normalization mismatch OR real fabrication where None is correct). | 17 restore-safe / 10 bad-citation / 19 verify. Only ~17 are an actual guard bug. | (a) split-and-ground each quote (the P8 fix). (b) EVIDENCE-QUOTING DISCIPLINE: model must cite verbatim — no bracketed insertions, no paraphrase (see new P10). (c) re-ground against raw text; some are true Nones. The re-run resolves all three correctly. | Deterministic (or re-ground in re-run)
2 | F9 encode. 1.P.CP.1.d ('work with others to discuss / investigate / solve / create') is being treated as separable (all-required) → wrong Partials. Ratified as an OR-list. | 33 rows across 40 lessons (~1/lesson). | Encode F9 as a GA worked-instance: OR-list, any one collaborative act → Full (consistent with F1). [DONE this session: SME-ratified + applied — 33 Partial->Full; see SME Rulings tab F9 + Corrections_Log.] | Rule-based
3 | needs_review under-firing. Borderline / low-confidence / grounding-rejected rows are not being flagged. | 9 TRUE in 1,023 rows (~0.9%). | Trip needs_review on: low confidence, grounding rejections, and F9-type list waffles. | Engine
4 | dense_score reporting anomaly (CONFIRM, likely cosmetic). dense_score = 0 on 7/11 lessons, BUT dense_rank is fully populated (100%) with distinct ranks on those same lessons → the retriever ran; RRF fuses by rank, so ranking is unaffected. Most likely a logging bug in the score column, NOT a recall failure. | 36 of 40 lessons dense_score all-zero, dense_rank intact on all → uniform 90% zero = logging artifact, not 36 independent retriever failures. Cosmetic. | Confirm with engineer whether dense_score is being logged/serialized correctly. No evidence it degraded results; do not block on it. | N/A (confirm)
CONFIRMED WORKING (do not re-open):
• CoT leak (P1) FIXED — 0 label/rationale mismatches outside the grounding bug across ALL 1,023 rows.
• P4 input_scope_caveat firing correctly on the close-read lessons (L3, L4, L5, L6, L7, L9).
• Adopted rulings landing correctly in the sample: F1, F2, F4, F5, F7, F8.
• Two-judge escalation (Opus/Sonnet) and the grounded/grounding_note columns are in place.

## Per-lesson counts
Per-lesson issue counts (all 40)
Lesson | Rows | P8 (grounding) | F9 (1.P.CP.1.d) | P4 caveats | dense=0? | needs_review
G1M2U1L1 | 25 | 1 | 1 | 0 |  | 0
G1M2U1L2 | 25 | 2 | 1 | 0 | yes | 0
G1M2U1L3 | 25 | 1 | 0 | 4 |  | 0
G1M2U1L4 | 25 | 0 | 0 | 3 | yes | 0
G1M2U1L5 | 25 | 1 | 1 | 2 | yes | 0
G1M2U1L6 | 26 | 2 | 0 | 7 |  | 1
G1M2U1L7 | 25 | 0 | 1 | 4 | yes | 0
G1M2U1L8 | 26 | 0 | 1 | 0 | yes | 0
G1M2U1L9 | 25 | 6 | 1 | 0 | yes | 0
G1M2U1L10 | 25 | 0 | 1 | 0 | yes | 0
G1M2U1L11 | 25 | 3 | 1 | 0 | yes | 0
G1M2U1L12 | 25 | 0 | 1 | 0 | yes | 0
G1M2U1L13 | 27 | 1 | 0 | 0 | yes | 0
G1M2U1L14 | 25 | 1 | 0 | 0 | yes | 0
G1M2U1L15 | 25 | 0 | 1 | 0 | yes | 0
G1M2U2L1 | 25 | 3 | 1 | 0 | yes | 1
G1M2U2L2 | 26 | 1 | 1 | 2 | yes | 3
G1M2U2L3 | 25 | 0 | 1 | 2 | yes | 2
G1M2U2L4 | 26 | 0 | 1 | 2 | yes | 0
G1M2U2L5 | 25 | 0 | 1 | 2 | yes | 0
G1M2U2L6 | 25 | 3 | 1 | 1 | yes | 0
G1M2U2L7 | 25 | 0 | 1 | 0 | yes | 0
G1M2U2L8 | 25 | 0 | 0 | 0 | yes | 0
G1M2U2L9 | 25 | 2 | 1 | 0 | yes | 1
G1M2U2L10 | 25 | 1 | 1 | 0 | yes | 0
G1M2U2L11 | 25 | 0 | 1 | 0 | yes | 0
G1M2U2L12 | 25 | 0 | 1 | 0 | yes | 0
G1M2U3L1 | 25 | 0 | 1 | 0 | yes | 0
G1M2U3L2 | 26 | 0 | 1 | 0 | yes | 0
G1M2U3L3 | 26 | 1 | 1 | 0 | yes | 0
G1M2U3L4 | 27 | 5 | 1 | 0 | yes | 0
G1M2U3L5 | 28 | 0 | 0 | 0 |  | 1
G1M2U3L6 | 25 | 1 | 1 | 0 | yes | 0
G1M2U3L7 | 25 | 2 | 1 | 0 | yes | 0
G1M2U3L8 | 28 | 1 | 1 | 0 | yes | 0
G1M2U3L9 | 27 | 1 | 1 | 0 | yes | 0
G1M2U3L10 | 27 | 7 | 1 | 0 | yes | 0
G1M2U3L11 | 28 | 0 | 1 | 0 | yes | 0
G1M2U3L12 | 25 | 0 | 1 | 0 | yes | 0
G1M2U3L13 | 25 | 0 | 1 | 0 | yes | 0
TOTAL | 1023 | 46 | 33 | 29 | 36 | 9

## SME Rulings (for overlay)
Veramynd — SME Rulings for the Overlay (living tracker; add rows as new fences surface)
How this works: the engine is framework-neutral and cannot decide standard-specific judgment calls (which lists are interchangeable, what 'met' requires). Those are SME rulings, encoded by the engineer as fenced worked-instances in the overlay. The tell that a ruling is missing: the model's 'Why' cell argues itself in a circle on a list-type standard. When that happens, it comes to the SME, not the engine's guess.
R1–R3 are already encoded in the overlay (Directive/Elicitation Exception; (I) read-aloud text-access; core-vs-supplemental / ELL-scaffold cap). The rows below are proposed additions — assign them R-numbers (R4+) on adoption.
ID | Standard | The question / symptom | SME ruling (encode in overlay) | Status | First seen | Re-validate against
F1 | 1.P.EICC.2.b | Are the four purposes (build knowledge / develop skills / make informed decisions / share information and ideas) interchangeable, or separable skills? Model waffles and contradicts its own label. | ADOPTED. Interchangeable OR-list, consistent with the 1.T.C.1.a purpose-list instance: a student using a text for ANY ONE of the four purposes satisfies the clause → Full. Do not dock for absent purposes. Keep the actor gate — the STUDENT must use the text for that purpose (discuss/apply/write), not passively hear a teacher read-aloud. (2.b is a broad engagement standard; discrimination lives in its siblings 2.a/2.c/2.d.) | ADOPTED — SME ratified | U1 L1, L3 | Gold set; re-score 2.b on all lessons
F2 | 1.L.V.1.b | (a) Are general/academic/specialized vocab interchangeable? (b) What counts as 'use to communicate'? (c) How to apply 'in a variety of settings'? Labels differed: L1 Partial, L3 None — on re-review this is a real distinction, not an error (see ruling). | ADOPTED (strict reading). (a) general/academic/specialized = interchangeable object-list; any one category counts; do NOT dock for absent academic/specialized. (b) 'use to communicate' = the STUDENT deploys grade-level/academic vocab in their own speech/writing: open frame with target vocab = thin → Partial; closed comprehension answer with a basic word = comprehension, not deployment → None; teacher-recited lyrics/echoing a just-defined word do NOT count. (c) 'in a variety of settings' = PER-LESSON scope cap: ≥2 settings → Full, single setting → Partial, none → None. Define 'settings' concretely: speaking/discussion, writing, and presenting are distinct; partner-talk + response-sheet writing = 2 settings. | ADOPTED — SME ratified (per-lesson reading) | U1 L1, L3 | Resolves L1 (Partial) & L3 (None) as BOTH correct; re-score 1.L.V.1.b on all lessons under strict reading
F3 | 1.P.EICC.2.d | Does 'interpret & construct texts TO AID THE ANALYSIS AND EVALUATION of texts and ideas' get met by observational noticing/wondering? Model over-aligns to Partial. | ADOPTED. The analysis/evaluation purpose is REQUIRED. If no activity has students use the text/their response to ANALYZE or EVALUATE texts or ideas → None (observational recording or a retell ≠ analysis). This is target-skill discrimination — crediting any interpret+construct collapses 2.d into 2.b/2.c. NOTE: 'required' does not mean always-None — 2.d is Partial/Full where students genuinely evaluate (e.g., peer critique against a quality checklist, analyzing a model text for craft). | ADOPTED — SME ratified | U1 L1, L3 | Re-score 2.d on all lessons (recurring over-alignment)
F4 | 1.T.T.1.a | Is 'characters, setting, major events, and dialogue' a separable-skills list (all required for Full) or interchangeable (any one)? | ADOPTED. Separable skills — Full requires all four (characters, setting, major events, dialogue); a lesson hitting only some = Partial. Matches the engine's separable-list rule and the model's correct L3 behavior. | ADOPTED — SME ratified | U1 L3 | Story-element lessons L3–L14
R1–R3 | (various) | Already encoded in the overlay. | Directive/Elicitation Exception · (I) read-aloud text-access channel · core-vs-supplemental (ELL-scaffold) cap. Listed for continuity. | Encoded | earlier | —
F5 | 1.T.T.1.e / all '(e.g., …)' standards | Parenthetical '(e.g., characters, settings, events)' lists — required components, or illustrative? | ADOPTED. Parenthetical '(e.g., …)' lists are ILLUSTRATIVE — meeting the core clause = Full; never dock for a missing e.g. item. Re-states engine Step-1 ('treat parenthetical examples as illustrations'); encode as a GA worked-instance so it applies to 1.T.T.1.e, 1.T.C.1.c, etc. | ADOPTED — SME ratified | U3 L5 | Re-score all 'e.g.' standards (1.T.T.1.e, 1.T.C.1.c, etc.)
F6 | 1.L.GC.1.10 / grammar in writing lessons | When a grammar/skill only appears AMBIENT/incidental in an activity built around a different objective (e.g., verbs appearing in a poem), is it Partial or None? | ADOPTED. A skill that appears only AMBIENT/incidental in an activity built around a different objective is None, not Partial (e.g., verbs appearing in a poem the lesson never teaches tense in). Re-states the engine's 'ambient → none' rule. | ADOPTED — SME ratified | U3 L5 | Re-score grammar standards in writing lessons
F7 | 1.T.T.2.* (Expository Techniques) | Genre gate on the expository Techniques substandards — does the 'individuals/events/ideas' object-list let 1.T.T.2.b apply to a narrative? | ADOPTED. 1.T.T.2.* (Expository Techniques) are genre-gated → None on a narrative text. The 'individuals/events/ideas' object-list inside 2.b does NOT override the expository genre gate; 2.b must match 2.a. Re-states the overlay's Techniques genre rule. | ADOPTED — SME ratified | U1 L6 | Re-score 1.T.T.2.* on all narrative lessons
F8 | 1.T.T.1.e (narrative creation, C) | Does writing/drawing about the events of a READ story (a retell/response sheet) meet 'use narrative techniques to CREATE texts'? | ADOPTED. A retell/response about a READ story is not creating an original narrative → None for 1.T.T.1.e; credit summarize (1.P.EICC.3.d) instead. Genuine narrative CREATION appears in Unit 3 (e.g., 'What the Moon Sees'). Apply F5 alongside: '(e.g., characters, settings, events)' is illustrative. | ADOPTED — SME ratified | U1 L6 | Re-score 1.T.T.1.e on retell/response lessons vs true-creation lessons
F9 | 1.P.CP.1.d (and similar collaboration lists) | 'Work with others to discuss topics, investigate questions, solve problems, and explore and create texts' — OR-list (any one) or separable (all required)? Updated run swung it to separable (Partial); prior run had it OR (Full). Now inconsistent with F1. LIVE in L2: rationale literally waffles — 'an OR-like list of collaborative purposes under one work-with-others umbrella, but each names a distinct collaborative act' — then scores Partial. That waffle IS the missing-ruling tell. | ADOPTED. OR-list (list of alternative collaborative activities under one verb phrase 'work with others'). Any ONE genuine, student-performed collaborative act satisfies the clause -> Full. Do NOT require all four (discuss / investigate / solve / explore-and-create) to co-occur, and do not dock for the absent ones. Consistent with F1's OR-list treatment and the overlay's 'range-of-target -> any one' rule. KEEP the student-actor gate: the STUDENT must do the collaborating (turn-and-talk, Think-Pair-Share, partner/small-group discussion, Science Talk, Back-to-Back/Face-to-Face). A teacher-only prompt with no student-facing collaborative task does NOT count. Most commonly satisfied by 'discuss topics' via a structured peer protocol. WORKED INSTANCE: U1 L8 1.P.CP.1.d -- 'Invite students to turn and talk with an elbow partner: "What does the author tell us about Papa? How would you describe him?"' -> students discuss a topic with a peer = one collaborative act -> Full (was Partial under the separable reading). | ADOPTED — SME ratified (Liz, this session) | U1 L8 (worked); +32 more | APPLIED: 1.P.CP.1.d re-scored across all 40 lessons -> 33 rows Partial->Full (2 already Full, 0 None). See Corrections_Log (F9-tagged, yellow).
Changelog:
• F2 revised to the STRICT reading after SME re-review of L3 1.L.V.1.b — L3 None is correct; my earlier 'FIX→Partial' was withdrawn. L1 Partial / L3 None are both correct.
• Added F5 (parenthetical e.g. = illustrative) and F6 (ambient grammar = None) from U3 L5. Confirmed F2 strict reading (1.L.V.1.b Full in a writing lesson).
• P4 CONFIRMED: Read-aloud Guides were not in the engine input → comprehension family under-scored on close-read lessons. Re-run required after adding the guides.
• P4 reframed: Read-aloud Guides were never provided by the client (separate EL 'Supporting Materials'), not omitted by the engineer. Treat close-read comprehension scores as understated; disclose to client and/or obtain the public guides.
• Added F7 (expository-Techniques genre gate) and F8 (retell ≠ narrative creation) from U1 L6. L6 is a close-read lesson → P4 caveat applies to its comprehension family.
• FINALIZED: F1 (2.b = OR-list, any one purpose, student-performed), F2 (per-lesson ≥2 settings), F3 (2.d analysis-purpose required), F4–F8 all ADOPTED by SME. Ready for the engineer to encode as GA worked-instances and re-validate against the gold set.
• Updated engine run reviewed (L1 sample): CoT leak gone (P1), F1/F7/F8 applied correctly, needs_review + grounded/grounding_note + input_scope_caveat columns added, two-judge escalation. New: F9 (1.P.CP.1.d OR-list) proposed; P8/P9 logged.
• L2 sample reviewed: F1/F5/F7/F8 all applied correctly. P8 grounding bug now confirmed zeroing 1.P.CP.2.a + 1.T.RA.2.a (→ escalated to TOP). P9: dense_score=0 across all L2 rows (dense retrieval likely failed). F9 waffle observed live.
• L3 re-run reviewed: P4 caveat column IMPLEMENTED and firing correctly on close-read comprehension standards (big win). F1/F2/F4/F7/F8 + R3 scaffold-cap all holding. P8 still present (1.P.CP.2.d) — this build has P4 but not yet the grounding fix. 1.P.EICC.4.c None on L3 is defensible (retell ≠ idea-generation; contrast L2 Full).

## Engine & Process Fixes
Engine / Process Fixes (not SME rulings — for the engineer to action)
ID | Issue | Fix | Priority | Status | First seen
P4 | INPUT-SCOPE LIMITATION (not an engine bug). The client provided only the 'Overview and Lessons' text; the Close/Focused Read-aloud Guides (which hold the text-dependent questions) live in EL Education's separate 'Supporting Materials' and were never provided. So close-read lessons were scored off only the thin recall questions in the lesson pages → comprehension family under-scored. | We cannot 're-run with the guides' — we don't have them. Two actions: (1) DISCLOSE + CAVEAT to the client: flag the affected comprehension standards on close-read lessons as 'scored on provided lesson text; likely understated pending the Read-aloud Guides.' (2) OBTAIN the guides — EL Education is an open/free curriculum; the guides are public Supporting Materials. If the client shares them (or authorizes pulling from the EL source), re-run the guided lessons. Do NOT hand-edit labels to compensate. Affected: 1.T.RA.2.a, 1.T.T.1.a/b/c, 1.P.EICC.3.d/e/f, 1.P.CP.2.d, 1.T.C.2.a on the guided read-aloud lessons. | TOP | CAVEAT COLUMN IMPLEMENTED & firing correctly (L3: input_scope_caveat populated on 1.T.T.1.c / 1.T.T.1.a / 1.T.RA.2.a / 1.P.CP.2.d). Engine-side mechanism DONE. Remaining action is the CLIENT disclosure + optionally obtaining the public EL guides. Confirmed limitation — disclose to client [VERIFIED by PDF spot-check: file is 'Overview and Lessons' only; Unit 1 flows directly into Unit 2 Overview with no Supporting-Materials/guide section; materials lists point to 'see supporting materials' elsewhere.] | U1 L3
P1 | Chain-of-thought leaks into the 'Why this alignment' cell and often contradicts the label ('…so this should be full' while labeled Partial). | Post-process to strip deliberation, leave only the final justification, AND reconcile the label to the reasoning's actual conclusion. | HIGH | ADDRESSED in updated run — rationales now clean/decisive | U1 L1, L3
P2 | Sheet uses a Confidence (High/Med/Low) column and no needs_review / ⚑ REVIEW flags = the pre-v5 engine. | Confirm engine version. Move to v5 (needs_review) so borderline calls (2.d, 1.L.V.1.b) are flagged, not buried as 'Low/Medium.' | HIGH | PARTLY ADDRESSED — needs_review column added; still under-firing (FALSE on the low-conf/rejected 1.L.V.1.b). Confirm trigger logic. | U1 L1, L3
P3 | Cross-lesson inconsistency: same standard + same evidence type, different label (1.L.V.1.b None in L3 vs Partial in L1). | Run the paired/consistency check across lessons before finalizing — same evidence type must get the same label. | MED | Open | U1 L3
P5 | One rationale invents a forbidden 'while reading vs after' timing requirement (1.P.EICC.3.d). | Remove timing-based reasoning (engine forbids invented timing requirements); score on target-skill grounds. | LOW | Open | U1 L3
P6 | Per-lesson substandard SELECTION is incomplete even in broad runs: U3 L5's peer-critique / Pinky-Partners Work Time went unscored on 1.P.EICC.4.f (evaluate via feedback), 1.P.CP.1.c (provide feedback), 1.P.CP.2.a (communicate/present). | Ensure the candidate-standard set per lesson covers activity-driven collaboration/feedback standards — not just writing/vocab/genre. | MED | Open | U3 L5
P7 (good) | NEW '[REJECTED: evidence missing or not found]' guard correctly caught fabricated/prior-lesson evidence and forced None (1.P.EICC.2.d, 1.P.AC.3.a/d). | Keep it. Only fix: strip the leftover chain-of-thought ('All clauses are met') that still precedes the reject tag, so the cell isn't self-contradictory (ties to P1). | LOW | FORMALIZED — now a first-class grounded/grounding_note column (see P8 for a bug in it) | U3 L5
P8 | Grounding guard over-rejects VALID concatenated multi-quote evidence → force-fails matched_status to none. CONFIRMED RECURRING & now hitting core standards: L1 zeroed 1.L.V.1.b; L2 zeroed 1.P.CP.2.a (rationale concludes present-aloud/manner-modifier → should be FULL) AND 1.T.RA.2.a (rationale concludes → should be PARTIAL). Both L2 rows are grounded=FALSE only because the evidence field joins multiple real quotes with ';' or '…'. STILL PRESENT in the L3 build: 1.P.CP.2.d wrongly None (rationale says 'partial') via ';'-joined multi-quote evidence. REFINED DIAGNOSIS: it's SEPARATE non-contiguous quotes joined with ';' that fail — a contiguous excerpt joined with '…' (e.g., 1.P.CP.2.a same lesson) can still ground. Fix must split on the quote delimiter and ground each piece. | Ground each quote INDEPENDENTLY (split the evidence field on ';' / '…'; normalize underscores, whitespace, curly quotes) before matching. This bug silently depresses presentation + comprehension scores across lessons. Add a regression test on multi-quote evidence. TOP priority — biggest score-integrity risk in the new pipeline. | TOP | Open | ALL 40: 46 rows (only 13 auto-correctable)
P9 | dense_score=0 on 7/11 Unit-1 lessons. CORRECTED READ: dense_rank is fully populated with distinct ranks on those lessons, so the retriever RAN — this is a logging artifact in the score column, not a recall failure (RRF fuses by rank). Demoted from 'top' to confirm-only. (Original P9 sub-item: 1.P.EICC.4.c none in L1 — recheck under re-run.) | Investigate why dense_score is 0 across an entire lesson (embedding step failed / not run). A 'none' with no retrieved candidates should route to needs_review or escalate, not silently land on none. Spot-audit standards that flipped full→none between runs. | LOW (confirm) | Open | ALL 40: dense=0 on 36/40 (uniform → logging artifact)
P10 | Evidence-quoting discipline. In ~10 grounding rejections the model inserted its own [bracketed notes] or PARAPHRASED the activity into the 'evidence' field instead of quoting verbatim, which correctly trips grounding. (Distinct from the concatenation bug.) The alignment is often right but the citation is unusable. | Constrain the evidence field to verbatim spans from the lesson text only — strip/forbid bracketed insertions and paraphrase; if the model must gloss, put it in the rationale, not evidence. | MED | Open (guard is catching it) | All 40